# Human–AI Collaboration Audit Lab

Progress estimate and remaining work

Status date: 21 October 2026 | Fictional governance scenarios only

# Overall estimate

Estimated completion: 60% | Estimated remaining: 40%. This is a practical project-management estimate, not a measured research metric. It separates preparation/documentation from evidence verification and final analysis.

| Workstream | Estimated status | What that means |
| --- | --- | --- |
| Protocol, research question and rubric | 90% complete | Design and scoring rules are documented; final consistency check still needed after eligibility decisions. |
| Scenario records and provisional scoring | 75% complete | Six fictional scenarios and provisional desk assessments are documented; scoring remains provisional and single-reviewer. |
| Prompt/source/provenance verification | 25% complete | Registers and rules exist, but exact prompts, source evidence and run metadata are not fully verified. |
| Primary paired A-versus-B analysis | 10% complete | No scenario is currently confirmed eligible; do not calculate or claim a primary paired effect yet. |
| Report, QA and submission packaging | 85% complete | Report, workbook, QA log and supporting documents are assembled; results may need updating after provenance checks. |

# Remaining work in order

1. Freeze and inventory original records. For each scenario, preserve the exact source evidence, task prompt, initial output, revision prompt, revised output and correction log. Record file/chat references; do not reconstruct missing items.

2. Verify eligibility. Check that A and B initial tasks use aligned evidence and requested outputs, and that B has a traceable initial response followed by revision. Keep unknown metadata marked unknown.

3. Decide scenario status. Mark each scenario eligible, pending or not eligible using the pre-defined gate. HG001 needs B-initial provenance; HG002 needs exact prompt/source alignment and its prior-context deviation documented; HG003–HG006 need record-level prompt/evidence/provenance checks.

4. Re-score only eligible records. Apply the 0–2 rubric consistently. Keep correction success N/A where no material initial error was identified. Keep the single-reviewer limitation explicit.

5. Run descriptive analysis. Compare A initial with B initial only for eligible pairs; separately compare B initial with B revised. Keep rubric dimensions separate and avoid inferential or causal claims.

6. Update report and package. Revise results, eligibility table, limitations, workbook, QA log and ZIP. Reopen files and test ZIP integrity before sharing.

# What is already done

Research question and fictional-task scope defined.

Six scenario evidence sets and the 0–2 rubric documented.

Provisional scenario-level findings and key numerical calculations recorded.

Provenance recovery pack and decision rules prepared.

Exploratory report, consolidated workbook, QA log and submission ZIP created.

# What must not be claimed yet

No scenario is currently confirmed eligible for the primary paired Condition A-versus-Condition B comparison. The current provisional HG003–HG006 scores are at the ceiling and show no measured score change; they do not establish that revision is ineffective or that outputs are error-free. No independent second-reviewer assessment has been performed.

# Completion estimate caveat

The 60% estimate reflects project readiness across protocol, documentation, data checks and analysis—not a claim that 60% of scientific evidence has been validated. If original prompts or outputs cannot be recovered, the study may need to be reported as a limited descriptive pilot rather than a clean paired A/B comparison.